## Ideal
Road Map - Ideal
|  | Key: |  |  | In Progress |  |  |  |  | Evaluation |  |  |  |  | Writing Up
ACTIVITY | PERIODS
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Machine Learning
Topic Modelling
Topic Labelling
Clustering
Extractive Summarisation
Abstractive Summarisation
Back End
Phase 1
Phase 2
Front End
Basic Skeleton
UI Upgrade
Second Platform
Report
Conclusion

## Minimal
Road Map - Minimal
|  | Key: |  |  | In Progress |  |  |  |  | Evaluation |  |  |  |  | Writing Up
ACTIVITY | PERIODS
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Machine Learning
Topic Modelling
Topic Labelling
Clustering
Extractive Summarisation
Abstractive Summarisation
Back End
Phase 1
Phase 2
Front End
Basic Skeleton
UI Upgrade
Second Platform
Report
Conclusion